BESS Scope of Engineering

- Cruz Bay BESS (Site 1 of 2; Site 2 is for Cruz Bay Generator Set)

Summary

Wärtsilä is offering an Engineering analysis for two battery energy storage systems (BESS) each at different sites on St. John. There are some key differences between the Engineering study of as it relates to the reciprocating engine power plant and the Engineering study of the BESS.

While for example , with the power plant, the engine sizing is already known, the BESS sizing will be determined as part of an Engineering study. Therefore, the BESS Engineering study must be divided in two sequential stages: “Stage 1 – Sizing Study” and “Stage 2 – Engineering.” The scope of Stage 2 can only begin after the confirmation from WAPA of the results from Stage 1.

Bearing in mind the importance of establishing a definitive project schedule, following completion of Stage 1,  Wärtsilä can optionally provide WAPA with a limited notice to proceed (LNTP) contract that would involve a down payment in order to secure the delivery of equipment with long delivery lead times – equipment such as batteries, inverters, and MV transformers    . The equipment quantities in the proposed LNTP contract would be determined during the “Stage 1 – Sizing Study” and the LNTP price will be based on the payment terms offered by the equipment OEMS. As a consequence, the price that would be associated with  the LNTP is not known at this time. The benefit of the LNTP contract approach to WAPA is that it begins the overall project delivery timeline prior to completion of Stage 2 of the BESS Engineering. The LNTP is optional, and alternatively WAPA can choose to begin procurement of battery equipment as part of a single contract signed at the end of the Engineering analysis.

Price

USD $450,000.

Includes Stage 1 and Stage 2 scope of supply listed below. Includes Coral Bay BESS and Cruz Bay BESS (on Site 1).

Estimated Timeline

- Stage 1 – Sizing Study: 		1 month from USVI input (detailed below)

- Optional LNTP: 			Immediately following Stage 1 results

- Stage 2 – Engineering: 		2 months from confirmation of “Stage 1 – Sizing Study”

- BESS Commercial Operation: 	9 months from equipment down payment / Optional LNTP

Note: timeline includes both BESS projects

Scope of Supply

Stage 1 – Sizing Study

  - USVI input

    - Site footprint

    - Interconnection details

    - Project term

    - Battery use case requirements (can be open discussion)

    - Design conditions (design temperature, power factor)

  - Wärtsilä deliverables

    - Use case modelling

    - Battery degradation analysis

    - Battery sizing optimization based on degradation analysis

    - Battery equipment selection and bill of materials

    - Indicative BESS pricing

Stage 2 – Engineering

- USVI input

  - Confirmation of Stage 1 Sizing Study results

- Wärtsilä deliverables

  - System SLD and Schematic

  - Site Layout options investigation and finalization

  - DC container drawing finalization in compliance with local codes and including confirmation of container dimensions, weights and connection points

  - Foundation design

  - Auxiliary power sizing and load calculation

  - Auxiliary power distribution including conductor sizing

  - Main MV circuit breaker preliminary specification

  - Site communication schematic and connection diagram

  - External preliminary low voltage, data and control wiring schematic

  - External preliminary cable routing for low voltage and data conductors

  - Preliminary MV cable loop conductor sizing and routing

  - Operational philosophy and system controls functional specification

  - Preliminary grounding grid study and sizing

  - DC conductor between DC container and PCS sizing and routing preliminary design

  - Auxiliary transformer selection and quotes, conduit/trench sizing and preliminary routing

  - MV POI protection and relay preliminary specification

  - Project schedule finalization and supply chain and logistic plan generation

  - Final BESS pricing